## FYP Gantt
HELP University ANPR Parking System Gantt Chart
Proposed schedule: September 2026 to April 2027. Intermediate dates are planning estimates, not confirmed deadlines.
Edit amber cells: task details, start/end dates, type and progress. Duration, date checks and weekly bars update automatically.
Progress is blank until entered. Green = planned work; purple M = milestone. Each column represents a Monday–Sunday week.
Timeline starts (Monday) |  |  | 2026-09-07 |  | 34 weeks shown; change D6 to move the timeline. Dates do not automatically reschedule dependent tasks.
Status date (editable) |  |  | 2026-09-27 |  | Red NOW marks the current week. Change D7 to update the marker. | [5 empty] | NOW
[9 empty] | Sep 26 |  |  |  | Oct 26 |  |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27
ID | Phase | Task / deliverable | Start | Finish | Days | Type | Progress | Date check | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26
1 | Research | Confirm scope and project proposal | 2026-09-10 | 2026-09-25 | 16 | Task |  | OK | bar: 2026-09-07 to 2026-09-21
2 | Requirements | Consult stakeholders and document requirements | 2026-09-14 | 2026-09-25 | 12 | Task | 100% | OK | bar: 2026-09-14 to 2026-09-21
3 | Research | Search and critically review 10–12 articles | 2026-09-14 | 2026-10-02 | 19 | Task |  | OK | bar: 2026-09-14 to 2026-09-28
4 | Research | Write literature synthesis and research gap | 2026-09-22 | 2026-10-04 | 13 | Task |  | OK | bar: 2026-09-21 to 2026-09-28
5 | Research | Submit literature review assignment | 2026-10-05 | 2026-10-05 | 0 | Milestone |  | OK | bar: 2026-10-05
6 | Design | Design system and deployment architecture | 2026-09-26 | 2026-10-05 | 10 | Task |  | OK | bar: 2026-09-21 to 2026-10-05
7 | Design | Design database, access rules and admin workflows | 2026-09-26 | 2026-10-05 | 10 | Task |  | OK | bar: 2026-09-21 to 2026-10-05
8 | Design | Complete requirements and design documentation | 2026-11-30 | 2026-11-30 | 0 | Milestone |  | OK | bar: 2026-11-30
9 | Development | Refine the admin interface prototype | 2026-09-18 | 2026-10-09 | 22 | Task |  | OK | bar: 2026-09-14 to 2026-10-05
10 | Development | Develop backend, database and admin login | 2026-09-28 | 2026-11-13 | 47 | Task |  | OK | bar: 2026-09-28 to 2026-11-09
11 | AI model | Obtain partner model and establish baseline | 2026-10-12 | 2026-10-30 | 19 | Task |  | OK | bar: 2026-10-12 to 2026-10-26
12 | AI model | Plan plate photo collection and get permission | 2026-10-19 | 2026-11-06 | 19 | Task |  | OK | bar: 2026-10-19 to 2026-11-02
13 | AI model | Collect Malaysian plate photos and label them | 2026-11-09 | 2026-12-18 | 40 | Task |  | OK | bar: 2026-11-09 to 2026-12-14
14 | AI model | Set aside test photos and make varied training copies | 2026-12-14 | 2026-12-31 | 18 | Task |  | OK | bar: 2026-12-14 to 2026-12-28
15 | AI model | Adapt and fine-tune the provided model | 2027-01-04 | 2027-02-05 | 33 | Task |  | OK | bar: 2027-01-04 to 2027-02-01
16 | AI model | Evaluate outdoor accuracy and analyse errors | 2027-02-08 | 2027-02-26 | 19 | Task |  | OK | bar: 2027-02-08 to 2027-02-22
17 | AI model | Complete model evaluation against 90% target | 2027-02-28 | 2027-02-28 | 0 | Milestone |  | OK | bar: 2027-02-22
18 | Development | Implement vehicle, permit and visitor management | 2027-01-04 | 2027-02-05 | 33 | Task |  | OK | bar: 2027-01-04 to 2027-02-01
19 | Development | Implement payment status and entry-exit records | 2027-01-25 | 2027-02-19 | 26 | Task |  | OK | bar: 2027-01-25 to 2027-02-15
20 | Integration | Prepare camera and barrier test environment | 2027-01-18 | 2027-02-12 | 26 | Task |  | OK | bar: 2027-01-18 to 2027-02-08
21 | Integration | Integrate recognition with parking access workflow | 2027-03-01 | 2027-03-19 | 19 | Task |  | OK | bar: 2027-03-01 to 2027-03-15
22 | Integration | Run pilot and resolve integration issues | 2027-03-22 | 2027-03-30 | 9 | Task |  | OK | bar: 2027-03-22 to 2027-03-29
23 | Integration | Complete integrated parking system | 2027-03-31 | 2027-03-31 | 0 | Milestone |  | OK | bar: 2027-03-29
24 | Testing | Prepare 20+ test cases and outdoor trial plan | 2027-03-08 | 2027-03-26 | 19 | Task |  | OK | bar: 2027-03-08 to 2027-03-22
25 | Testing | Run functional and repeated outdoor trials | 2027-04-01 | 2027-04-16 | 16 | Task |  | OK | bar: 2027-03-29 to 2027-04-12
26 | Testing | Fix defects, retest and evaluate performance | 2027-04-19 | 2027-04-26 | 8 | Task |  | OK | bar: 2027-04-19 to 2027-04-26
27 | Reporting | Write methods, implementation and results chapters | 2026-11-02 | 2027-04-23 | 173 | Task |  | OK | bar: 2026-11-02 to 2027-04-19
28 | Reporting | Prepare final report, demonstration and presentation | 2027-04-19 | 2027-04-29 | 11 | Task |  | OK | bar: 2027-04-19 to 2027-04-26
29 | Reporting | Complete testing and final project review | 2027-04-30 | 2027-04-30 | 0 | Milestone |  | OK | bar: 2027-04-26
Schedule basis |  | Assignment deadline: 5 October 2026. Objective milestones: design November 2026, AI February 2027, integration March 2027, testing April 2027.
Planning assumptions |  | Detailed dates are estimates. Stakeholder requirements were gathered early; September 14–25 is a planning allocation. Confirm final report dates.
Data and model |  | Model training depends on partner weights/code and usable Malaysian images. Keep the evaluation set separate from training and tuning.
Dependencies |  | Backend, database and login start with mock plate results; they do not wait for the partner model. Model training still depends on model delivery and data.
Testing targets |  | Proposed: 90% complete-plate accuracy, response time below 3 seconds, and 95% operational reliability. Agree measurement definitions with the supervisor.
Editing |  | Use real Excel dates in Start and Finish. Set milestones to the same start/end date. Days are inclusive calendar days; milestones have zero duration.
Progress |  | Enter 0%–100% yourself. It is a tracking field only; green bars show the planned schedule, not actual completion.
More tasks |  | Insert and copy a complete task row within the schedule to preserve formulas and formatting, then change its ID, details and dates.
Source |  | Project proposal and objectives supplied in this conversation. All detailed task dates are suggested planning allocations.